## Wordpress Site
Wordpress Project
Making our Wordpress Templates ready …
Create a Repo on github give an arbitary name such as Wordpress Site-X
Install the wordpress default framework in it
Setup decided domain and decided theme (adding content, images etc)
Setup Appropriate Logo and Favicon
Setup Admin Portal / Backoffice (add users etc)
Check efficient way of deploying Wordpress site on different env
Deployment on Dev Env., QA and Prodc Envs
Document the generic steps taken to achieve the above tasks
What we will do when customer comes for this type of Website ….
Create a repo with the customer name
Create a project directory with customer name
Clone this created repo
Install the wordpress default framework in it
Setup / customize customer choice theme (add content, images etc)
Setup customer logo and favicon
Add customer content, images etc
Push code in dedicated branch
Extract QA branch from the dedicated branch and deploy it on QA env.
Upon Passing from QA deploy it on Demo env.
Upon Passing from Demo env. Deploy it on customer machine

## Shopify Site
Shopify Project
Making our Shopify Templates ready …
Create a Repo on github give an arbitary name such as Shopify Site-X
Install the Shopify default framework in it
Setup Appropriate Logo and Favicon
Setup decided domain and decided theme (adding products, categories, content, images etc)
Setup Admin Portal / Backoffice (add users etc)
Check efficient way of deploying Shopify site on different env
Deployment on Dev Env., QA and Prodc Envs
Document the generic steps taken to achieve the above tasks
What we will do when customer comes for this type of Ecommerce Website ….
Create a repo with the customer name
Create a project directory with customer name
Clone this created repo
Install the shopify default framework in it
Setup / customize customer choice theme
Setup customer logo and favicon
Add customer products, categories, content, images and relvant info etc
Push code in dedicated branch
Extract QA branch from the dedicated branch and deploy it on QA env.
Upon Passing from QA deploy it on Demo env.
Upon Passing from Demo env. Deploy it on customer machine

## Raw Dev - Business Site
Raw Development - Business Site
Steps towards target
How to Develop ….
Create a Repo on github give an arbitary name such as Structure-X
Create Website structure on React which contains Home, About Us, Products, Blogs, Carrier and Contact Us Pages | What if, we can make it dynamic as well saving structure in db and render it as per the request
Each page have a certain design / theme in which sections are specified (such as Logo, Nav Bar, Slider, Content Section, Form section, Email subscription section, Image grids and Video Player etc) and it is robust enough that it can hold re-usable components and sections
Contact Us and Blog Page sections should be attached with APIs
Approach-1 or Approach 2 of adding re-usable components
Sections such as contact us forms, add blog forms should contain the configurable API URLs
Create another Repo of Test Demo website in which these section / components are placed on our structure
What we will do when customer comes for this type of Website ….
Create a project directory with customer name
Clone the Structure-X repo and create any dedicated (later on we can create Dev and QA branches, so that code in branch will be dedicated to that customer) branch
Copy the mongodb database schema into a new database for this customer
Add content of re-usable components w.r.t customer using insert scripts
Place the sections and components in the structure according to the customer choice
Create build and deploy all the components (front-end,back-end and db) it on QA server to Test (both front-end and back-end i-e NodeJS) | Pipleline is required
Upon Passing from QA deploy it on Demo env.
Upon Passing from Demo env. Deploy it on customer machine
How to Develop specifying it ….

## Raw Dev - Ecom Site
Raw Development - Business Site
Steps towards target
How to Develop ….
Create a Repo on github give an arbitary name such as Ecomm Structure -X
Create Ecommerce website structure on React which contains the standard Ecommerce pages such as Products page, Customer Care, Check Out page, Login and Signup | What if, we can make it dynamic as well saving structure in db and render it as per the request
Each page have a standard design / theme of an Ecommerce site in which sections are specified (such as Logo, Nav Bar, Product list, Category List, Slider, Content Section, Form section, Email subscription section and it is robust enough that it can hold re-usable components and sections
Login, Signup, Product list, Category list sections should be attached with APIs
Create a NodeJS Server which contain Login and Signup, Product list and Category list operations
Maintaine repo of pre-built Login and Signup forms, Product list, Category list, Sliders, Nav Bar, Forms, Email subscriber section
Decide the method of placing these sections / components into the structure defined above
Sections such as Login and Signup forms should contain the configurable API URLs
Create another Repo of Test Demo Ecommerce website in which these section / components are placed on our structure also populate dummy product and categories in it using Db scripts
What we will do when customer comes for this type of Website ….
Create a project directory with customer name
Clone the Ecomm-X repo and create any dedicated (later on we can create Dev and QA branches, so that code in branch will be dedicated to that customer) branch
Place the sections and components in the structure according to the customer choice
Populate Customer's product and categories using Db scripts
Create build and deploy it on QA server to Test (both front-end and back-end i-e NodeJS) | Pipleline is required
Upon Passing from QA deploy it on Demo env.
Upon Passing from Demo env. Deploy it on customer machine

## Raw Dev Busines Site - Approach
Basic Level | Medium Level | Advance Level
Re-usable components will be placed in the repo and should be copy paste inside the structure manually everytime, but challenge will be if we want some sort of change. We have to do the changes and deploy it again and again | Re-usable components will contain html and css classes or may be css files as well. For this part we have two options either putting css files of re-usable components along with structure files, Secondly we should put css files of re-usable components along with the re-usable components. | With all the capabilities of Medium Level Approach 1 what if, if we save the entire html, css of our raw dev structure in the schema as well and assigning it types
Re-usable components will contain html and css classes or may be css files as well. For this part we have two options either putting css files of re-usable components along with structure files, Secondly we should put css files of re-usable components along with the re-usable components. | Approach 1 | For Demo site Contact Us Forms, Login Signup Forms should be handle in a sense that It will not call APIs
Thought about the scheme to identify this re-usable components | Re-usable components can be place in the mongo and fetch via APIs but challenge will be to minimze the render time. Robust schema should be consider in order to cover all the requirements of any re-usable components. Such as to place the navigation bar we have to look for its hyper link value etc. Aslo our schema is robust enough that it can contain the content. This approach of saving re-usable components will also help in rendering them on our another project of Inertiasoft Re-usable components repository | Re-usable components will contain html and css classes or may be css files as well. For this part we have two options either putting css files of re-usable components along with structure files, Secondly we should put css files of re-usable components along with the re-usable components.
For Demo site Contact Us Forms, Login Signup Forms should be handle in a sense that It will not call APIs | A nodejs server will be created of handling re-usable components
We have to list down first, how many re-usable components we are looking for. Then we will design the schema for each
Fast performance APIs will be built to achieve this also passing data between back-end and front-end should not disturb the html and css of these re-usable components
Each structure will know what re-usable components APIs should it call
Later on after MVP we will design the forms / interface to add the re-usable components inside the mongo. Bur for MVP we will be doing using insert script
We should use cache techniques to enhance the performance of binding re-usable components to front-end from back-end
APIs should take structure name or identifer in order to differentiate them while binding the re-usable components
CSS files should be contain by the structure it self, re-usable components saved inside mongo will only contain the class and ids
To save the content of each re-usable components w.r.t customer will be handle by creating and configuring customer's own database. For now (this MVP) we will add content using insert scripts
APIs can be authenticated using the database user
Approach 2
We will use github repository and npm plugin to store and organize the re-usable components files. This will help in adding re-usable compnents to our pre-built structure by executing npm install commands. This addition will be once at a time no need to get re-usable components everytime via API calls.
For this we have to manage the identification of re-usable components by developing custom logic
For this we will add content in the re-usable component after adding them using the npm install command
This will help in avoiding node server if website has no requirement of dynamic site
For Demo site Contact Us Forms, Login Signup Forms should be handle in a sense that It will not call APIs

## Raw Dev Ecomm Site - Approach
Approach
Make use of code base of Vendure to build the basic ecommerce project
Execute approach 1 or 2 in order to adding the re-usable components

## Task List
Learn KOA
Learn React
RND of Mongo Servers choice of own mongo server
Sit with asjad to check the injection of re-usable components
Ask management to list the re-usable component we will provide
Ask management to share the theme idea for wordpress business site, ecommerce site, raw dev business site, raw ecommerce site
Providing hosting machines to create enviornments.
Search for re-usable components (plagirism and copyright should be consider)

## Sheet2
Nav Bars | https://www.mockplus.com/blog/post/bootstrap-navbar-template | For Demo site Contact Us Forms, Login Signup Forms, Check Out process should be handle in a sense that It will not call APIs
Create a database on Mongo which is capable of storing re-usable components and content
Create a NodeJS Server which contain the APIs to pull the re-usable components and content as well as CRUD operations regarding the Contact Us and Blogs feature as well as

## InertiaSft Repo Site - Approach
Approach
Create structure similarly as in Raw Dev Business Site
Execute Approach 1 or 2